## Daily Gantt Chart Template
2ND DAILY GANTT CHART
Team Horizon | [6 empty] | Daniel Neagu | [16 empty] | 2022-03-08 |  |  |  |  | 2022-05-10
PROJECT NAME: Final Year Allocation Project. | [6 empty] | CLIENT NAME | [16 empty] | START DATE |  |  |  |  | END DATE
Task ID | Task Name | Assigned to | Start Date | End Date | Duration (In Days) | time axis 2022-03-08 to 2022-05-10
T01 | Final Version of Code | Hamza Javed | 2022-03-10 | 2022-04-16 | 37 | bar: 2022-03-10 to 2022-04-16
T02 | Unit Testing/Code Inspection Document | Hamza Javed | 2022-04-17 | 2022-04-18 | 1 | bar: 2022-04-17 to 2022-04-18
T03 | Acceptance Testing Document | Adnan Qureshi, Hamza Javed | 2022-04-17 | 2022-04-19 | 2 | bar: 2022-04-17 to 2022-04-19
T04 | Story Cards | Mohammed Ghafori | 2022-05-01 | 2022-05-03 | 2 | bar: 2022-05-01 to 2022-05-03
T05 | Meeting Minutes | Mohammed Ghafori | 2022-05-01 | 2022-05-03 | 2 | bar: 2022-05-01 to 2022-05-03

## ©
© TemplateLab.com